## Dev Schedule
Development Plan
Note: This is an estimatation of the time required mostly project is completed before the due date. Only working days are counted.
Important: We ask 20% upfront payment.
Upflence web site | Activity |  |  | Days Required | Total Days | Budgets(k)
| Web | Upfluence Flow | Upfluence Understanding(www.upfluence.com) | 1 | 1 | 1
|  |  | Project Setting | 1 | 2
|  |  | Task Assigning | 1 | 3
|  |  | Feedback | 1 | 4
|  |  | Prepare to start | 1 | 5
|  | Design | Upfluence User Interface(UI) | 9 | 14 | 2
|  |  | UI Approval from the client | 1 | 15
|  | Development | Front-end Development | 10 | 25 | 4
|  |  | Back-end Development | 5 | 30 | 2
|  |  | Front-end/Back-end Intergration | 5 | 35 | 1
|  | Finalizing | Server Management | 3 | 38 | 1
|  |  | Testing | 2 | 40 | 1
[5 empty] | 40 Days | 12 (k)